## Risk List
[8 empty] | закупка оборудования |  |  | Responsible: <insert name here>
ID | Risk Title | Date | Rank | Rel | Prob | Impact | Exp | Effect | Mitigation - превентивные | Trigger Event | Contingency - компенсационные мероприятия
1 | срыв срока заключения договора с УПК | еженедельно |  |  | 50% | 8 | 4 | сдвиг сроков начала обучения | расширить зону поиска организации по обучению пилотов, запланировать срок поиска на ранний срок (за 2 недели) | не выбран поставщик услуг на 12 неделе. | пересмотр требований к поставщику,создать собственный УЦ
2 | техническая неисправность летательного аппарата | ежедневный |  |  | 50% | 9 | 4.5 | несчастный случай, сдвиг сроков пилотного запуска | ежедневная диагностика летательного аппарата, создание резерва запчастей | обнаружение неисправности узлов летательного аппарата за день до начала испытаний | разработка альтернативного летательного аппарата "СТУПА"
3 | сокращение сроков подбора персонала | ежедневно |  |  | 20% | 3 | 0.6 | сокращение срока окончания по подбору персонала, увеличение срока подготовки пилотов |  | процент набранного персонала за один день в течении недели | уменьшение затрат на подбор персонала
Note on C2: Date the risk was identified
Note on D2: Rank of this risk. A risk will have a higher rank if it has become more likely, has occurred, or if the team feels it is in some way more important than other risks. This is a subjective measure.
Note on E2: Release that this risk affects. This could be used for tracking risks specific to a cycle in a spiral development project for example.
Note on F2: Probability that this event will occur
Note on G2: Relative Impact of the event. 1-10
Note on H2: The product of the Prob and Impact fields. Higher numbers are bad.
Note on I2: What adverse events can be expected if risk occurs?
Note on J2: What actions can we take to avoid having the risk event occur?
Note on K2: How do we know when the risk event has happened? What indications can we look for?
Note on L2: If the event occurs, what can we do to limit the effects of the risk?

## Лист1
Risk Title | Date | Rank | Rel | Prob | Impact- | Exp- | Impact+ | Exp+ | Effect
Повышение валютного курса более чем на 10% |  |  |  | 70% | 8 | 5.6 | 5 | 3.5 | - негативный: повышение стоимости импортируемых комплектующих - снижение относит. Стоимости трудовых ресурсов
Note on C4: Date the risk was identified
Note on D4: Rank of this risk. A risk will have a higher rank if it has become more likely, has occurred, or if the team feels it is in some way more important than other risks. This is a subjective measure.
Note on E4: Release that this risk affects. This could be used for tracking risks specific to a cycle in a spiral development project for example.
Note on F4: Probability that this event will occur
Note on G4: Relative Impact of the event. 1-10
Note on H4: The product of the Prob and Impact fields. Higher numbers are bad.
Note on K4: What adverse events can be expected if risk occurs?

## Risk Matrix
Risk Matrix
Impact | 9-10 | 0 | 0 | 1 | 0 | 0
| 7-8 | 0 | 0 | 1 | 0 | 0
| 5-6 | 0 | 0 | 0 | 0 | 0 | Zone Total: 1
| 3-4 | 1 | 0 | 0 | 0 | 0 | Zone Total: 1
| 1-2 | 0 | 0 | 0 | 0 | 0 | Zone Total: 1
|  | 1-20% | 21-40% | 41-60% | 61-80% | 81-100%
Probability

## CriteriaSheet
Do NOT Edit this sheet. This sheet provides the formulas for the Matrix Sheet
1-2 |  |  |  |  | 3-4 |  |  |  |  | 5-6 |  |  |  |  | 7-8 |  |  |  |  | 9-10
1-20% |  |  |  |  | 1-20% |  |  |  |  | 1-20% |  |  |  |  | 1-20% |  |  |  |  | 1-20%
Prob | Impact | Prob | Impact | Result | Prob | Impact | Prob | Impact | Result | Prob | Impact | Prob | Impact | Result | Prob | Impact | Prob | Impact | Result | Prob | Impact | Prob | Impact | Result
1% | 1 | 1% | 2 | 0 | 1% | 3 | 1% | 4 | 1 | 1% | 5 | 1% | 6 | 0 | 1% | 7 | 1% | 8 | 0 | 1% | 9 | 1% | 10 | 0
2% | 1 | 2% | 2 |  | 2% | 3 | 2% | 4 |  | 2% | 5 | 2% | 6 |  | 2% | 7 | 2% | 8 |  | 2% | 9 | 2% | 10
3% | 1 | 3% | 2 |  | 3% | 3 | 3% | 4 |  | 3% | 5 | 3% | 6 |  | 3% | 7 | 3% | 8 |  | 3% | 9 | 3% | 10
4% | 1 | 4% | 2 |  | 4% | 3 | 4% | 4 |  | 4% | 5 | 4% | 6 |  | 4% | 7 | 4% | 8 |  | 4% | 9 | 4% | 10
5% | 1 | 5% | 2 |  | 5% | 3 | 5% | 4 |  | 5% | 5 | 5% | 6 |  | 5% | 7 | 5% | 8 |  | 5% | 9 | 5% | 10
6% | 1 | 6% | 2 |  | 6% | 3 | 6% | 4 |  | 6% | 5 | 6% | 6 |  | 6% | 7 | 6% | 8 |  | 6% | 9 | 6% | 10
7% | 1 | 7% | 2 |  | 7% | 3 | 7% | 4 |  | 7% | 5 | 7% | 6 |  | 7% | 7 | 7% | 8 |  | 7% | 9 | 7% | 10
8% | 1 | 8% | 2 |  | 8% | 3 | 8% | 4 |  | 8% | 5 | 8% | 6 |  | 8% | 7 | 8% | 8 |  | 8% | 9 | 8% | 10
9% | 1 | 9% | 2 |  | 9% | 3 | 9% | 4 |  | 9% | 5 | 9% | 6 |  | 9% | 7 | 9% | 8 |  | 9% | 9 | 9% | 10
10% | 1 | 10% | 2 |  | 10% | 3 | 10% | 4 |  | 10% | 5 | 10% | 6 |  | 10% | 7 | 10% | 8 |  | 10% | 9 | 10% | 10
11% | 1 | 11% | 2 |  | 11% | 3 | 11% | 4 |  | 11% | 5 | 11% | 6 |  | 11% | 7 | 11% | 8 |  | 11% | 9 | 11% | 10
12% | 1 | 12% | 2 |  | 12% | 3 | 12% | 4 |  | 12% | 5 | 12% | 6 |  | 12% | 7 | 12% | 8 |  | 12% | 9 | 12% | 10
13% | 1 | 13% | 2 |  | 13% | 3 | 13% | 4 |  | 13% | 5 | 13% | 6 |  | 13% | 7 | 13% | 8 |  | 13% | 9 | 13% | 10
14% | 1 | 14% | 2 |  | 14% | 3 | 14% | 4 |  | 14% | 5 | 14% | 6 |  | 14% | 7 | 14% | 8 |  | 14% | 9 | 14% | 10
15% | 1 | 15% | 2 |  | 15% | 3 | 15% | 4 |  | 15% | 5 | 15% | 6 |  | 15% | 7 | 15% | 8 |  | 15% | 9 | 15% | 10
16% | 1 | 16% | 2 |  | 16% | 3 | 16% | 4 |  | 16% | 5 | 16% | 6 |  | 16% | 7 | 16% | 8 |  | 16% | 9 | 16% | 10
17% | 1 | 17% | 2 |  | 17% | 3 | 17% | 4 |  | 17% | 5 | 17% | 6 |  | 17% | 7 | 17% | 8 |  | 17% | 9 | 17% | 10
18% | 1 | 18% | 2 |  | 18% | 3 | 18% | 4 |  | 18% | 5 | 18% | 6 |  | 18% | 7 | 18% | 8 |  | 18% | 9 | 18% | 10
19% | 1 | 19% | 2 |  | 19% | 3 | 19% | 4 |  | 19% | 5 | 19% | 6 |  | 19% | 7 | 19% | 8 |  | 19% | 9 | 19% | 10
20% | 1 | 20% | 2 |  | 20% | 3 | 20% | 4 |  | 20% | 5 | 20% | 6 |  | 20% | 7 | 20% | 8 |  | 20% | 9 | 20% | 10
21-40% |  |  |  |  | 21-40% |  |  |  |  | 21-40% |  |  |  |  | 21-40% |  |  |  |  | 21-40%
Prob | Impact | Prob | Impact | Result | Prob | Impact | Prob | Impact | Result | Prob | Impact | Prob | Impact | Result | Prob | Impact | Prob | Impact | Result | Prob | Impact | Prob | Impact | Result
21% | 1 | 21% | 2 | 0 | 21% | 3 | 21% | 4 | 0 | 21% | 5 | 21% | 6 | 0 | 21% | 7 | 21% | 8 | 0 | 21% | 9 | 21% | 10 | 0
22% | 1 | 22% | 2 |  | 22% | 3 | 22% | 4 |  | 22% | 5 | 22% | 6 |  | 22% | 7 | 22% | 8 |  | 22% | 9 | 22% | 10
23% | 1 | 23% | 2 |  | 23% | 3 | 23% | 4 |  | 23% | 5 | 23% | 6 |  | 23% | 7 | 23% | 8 |  | 23% | 9 | 23% | 10
24% | 1 | 24% | 2 |  | 24% | 3 | 24% | 4 |  | 24% | 5 | 24% | 6 |  | 24% | 7 | 24% | 8 |  | 24% | 9 | 24% | 10
25% | 1 | 25% | 2 |  | 25% | 3 | 25% | 4 |  | 25% | 5 | 25% | 6 |  | 25% | 7 | 25% | 8 |  | 25% | 9 | 25% | 10
26% | 1 | 26% | 2 |  | 26% | 3 | 26% | 4 |  | 26% | 5 | 26% | 6 |  | 26% | 7 | 26% | 8 |  | 26% | 9 | 26% | 10
27% | 1 | 27% | 2 |  | 27% | 3 | 27% | 4 |  | 27% | 5 | 27% | 6 |  | 27% | 7 | 27% | 8 |  | 27% | 9 | 27% | 10
28% | 1 | 28% | 2 |  | 28% | 3 | 28% | 4 |  | 28% | 5 | 28% | 6 |  | 28% | 7 | 28% | 8 |  | 28% | 9 | 28% | 10
29% | 1 | 29% | 2 |  | 29% | 3 | 29% | 4 |  | 29% | 5 | 29% | 6 |  | 29% | 7 | 29% | 8 |  | 29% | 9 | 29% | 10
30% | 1 | 30% | 2 |  | 30% | 3 | 30% | 4 |  | 30% | 5 | 30% | 6 |  | 30% | 7 | 30% | 8 |  | 30% | 9 | 30% | 10
31% | 1 | 31% | 2 |  | 31% | 3 | 31% | 4 |  | 31% | 5 | 31% | 6 |  | 31% | 7 | 31% | 8 |  | 31% | 9 | 31% | 10
32% | 1 | 32% | 2 |  | 32% | 3 | 32% | 4 |  | 32% | 5 | 32% | 6 |  | 32% | 7 | 32% | 8 |  | 32% | 9 | 32% | 10
33% | 1 | 33% | 2 |  | 33% | 3 | 33% | 4 |  | 33% | 5 | 33% | 6 |  | 33% | 7 | 33% | 8 |  | 33% | 9 | 33% | 10
34% | 1 | 34% | 2 |  | 34% | 3 | 34% | 4 |  | 34% | 5 | 34% | 6 |  | 34% | 7 | 34% | 8 |  | 34% | 9 | 34% | 10
35% | 1 | 35% | 2 |  | 35% | 3 | 35% | 4 |  | 35% | 5 | 35% | 6 |  | 35% | 7 | 35% | 8 |  | 35% | 9 | 35% | 10
36% | 1 | 36% | 2 |  | 36% | 3 | 36% | 4 |  | 36% | 5 | 36% | 6 |  | 36% | 7 | 36% | 8 |  | 36% | 9 | 36% | 10
37% | 1 | 37% | 2 |  | 37% | 3 | 37% | 4 |  | 37% | 5 | 37% | 6 |  | 37% | 7 | 37% | 8 |  | 37% | 9 | 37% | 10
38% | 1 | 38% | 2 |  | 38% | 3 | 38% | 4 |  | 38% | 5 | 38% | 6 |  | 38% | 7 | 38% | 8 |  | 38% | 9 | 38% | 10
39% | 1 | 39% | 2 |  | 39% | 3 | 39% | 4 |  | 39% | 5 | 39% | 6 |  | 39% | 7 | 39% | 8 |  | 39% | 9 | 39% | 10
40% | 1 | 40% | 2 |  | 40% | 3 | 40% | 4 |  | 40% | 5 | 40% | 6 |  | 40% | 7 | 40% | 8 |  | 40% | 9 | 40% | 10
41-60% |  |  |  |  | 41-60% |  |  |  |  | 41-60% |  |  |  |  | 41-60% |  |  |  |  | 41-60%
Prob | Impact | Prob | Impact | Result | Prob | Impact | Prob | Impact | Result | Prob | Impact | Prob | Impact | Result | Prob | Impact | Prob | Impact | Result | Prob | Impact | Prob | Impact | Result
41% | 1 | 41% | 2 | 0 | 41% | 3 | 41% | 4 | 0 | 41% | 5 | 41% | 6 | 0 | 41% | 7 | 41% | 8 | 1 | 41% | 9 | 41% | 10 | 1
42% | 1 | 42% | 2 |  | 42% | 3 | 42% | 4 |  | 42% | 5 | 42% | 6 |  | 42% | 7 | 42% | 8 |  | 42% | 9 | 42% | 10
43% | 1 | 43% | 2 |  | 43% | 3 | 43% | 4 |  | 43% | 5 | 43% | 6 |  | 43% | 7 | 43% | 8 |  | 43% | 9 | 43% | 10
44% | 1 | 44% | 2 |  | 44% | 3 | 44% | 4 |  | 44% | 5 | 44% | 6 |  | 44% | 7 | 44% | 8 |  | 44% | 9 | 44% | 10
45% | 1 | 45% | 2 |  | 45% | 3 | 45% | 4 |  | 45% | 5 | 45% | 6 |  | 45% | 7 | 45% | 8 |  | 45% | 9 | 45% | 10
46% | 1 | 46% | 2 |  | 46% | 3 | 46% | 4 |  | 46% | 5 | 46% | 6 |  | 46% | 7 | 46% | 8 |  | 46% | 9 | 46% | 10
47% | 1 | 47% | 2 |  | 47% | 3 | 47% | 4 |  | 47% | 5 | 47% | 6 |  | 47% | 7 | 47% | 8 |  | 47% | 9 | 47% | 10
48% | 1 | 48% | 2 |  | 48% | 3 | 48% | 4 |  | 48% | 5 | 48% | 6 |  | 48% | 7 | 48% | 8 |  | 48% | 9 | 48% | 10
49% | 1 | 49% | 2 |  | 49% | 3 | 49% | 4 |  | 49% | 5 | 49% | 6 |  | 49% | 7 | 49% | 8 |  | 49% | 9 | 49% | 10
50% | 1 | 50% | 2 |  | 50% | 3 | 50% | 4 |  | 50% | 5 | 50% | 6 |  | 50% | 7 | 50% | 8 |  | 50% | 9 | 50% | 10
51% | 1 | 51% | 2 |  | 51% | 3 | 51% | 4 |  | 51% | 5 | 51% | 6 |  | 51% | 7 | 51% | 8 |  | 51% | 9 | 51% | 10
52% | 1 | 52% | 2 |  | 52% | 3 | 52% | 4 |  | 52% | 5 | 52% | 6 |  | 52% | 7 | 52% | 8 |  | 52% | 9 | 52% | 10
53% | 1 | 53% | 2 |  | 53% | 3 | 53% | 4 |  | 53% | 5 | 53% | 6 |  | 53% | 7 | 53% | 8 |  | 53% | 9 | 53% | 10
54% | 1 | 54% | 2 |  | 54% | 3 | 54% | 4 |  | 54% | 5 | 54% | 6 |  | 54% | 7 | 54% | 8 |  | 54% | 9 | 54% | 10
55% | 1 | 55% | 2 |  | 55% | 3 | 55% | 4 |  | 55% | 5 | 55% | 6 |  | 55% | 7 | 55% | 8 |  | 55% | 9 | 55% | 10
56% | 1 | 56% | 2 |  | 56% | 3 | 56% | 4 |  | 56% | 5 | 56% | 6 |  | 56% | 7 | 56% | 8 |  | 56% | 9 | 56% | 10
57% | 1 | 57% | 2 |  | 57% | 3 | 57% | 4 |  | 57% | 5 | 57% | 6 |  | 57% | 7 | 57% | 8 |  | 57% | 9 | 57% | 10
58% | 1 | 58% | 2 |  | 58% | 3 | 58% | 4 |  | 58% | 5 | 58% | 6 |  | 58% | 7 | 58% | 8 |  | 58% | 9 | 58% | 10
59% | 1 | 59% | 2 |  | 59% | 3 | 59% | 4 |  | 59% | 5 | 59% | 6 |  | 59% | 7 | 59% | 8 |  | 59% | 9 | 59% | 10
60% | 1 | 60% | 2 |  | 60% | 3 | 60% | 4 |  | 60% | 5 | 60% | 6 |  | 60% | 7 | 60% | 8 |  | 60% | 9 | 60% | 10
61-80% |  |  |  |  | 61-80% |  |  |  |  | 61-80% |  |  |  |  | 61-80% |  |  |  |  | 61-80%
Prob | Impact | Prob | Impact | Result | Prob | Impact | Prob | Impact | Result | Prob | Impact | Prob | Impact | Result | Prob | Impact | Prob | Impact | Result | Prob | Impact | Prob | Impact | Result
61% | 1 | 61% | 2 | 0 | 61% | 3 | 61% | 4 | 0 | 61% | 5 | 61% | 6 | 0 | 61% | 7 | 61% | 8 | 0 | 61% | 9 | 61% | 10 | 0
62% | 1 | 62% | 2 |  | 62% | 3 | 62% | 4 |  | 62% | 5 | 62% | 6 |  | 62% | 7 | 62% | 8 |  | 62% | 9 | 62% | 10
63% | 1 | 63% | 2 |  | 63% | 3 | 63% | 4 |  | 63% | 5 | 63% | 6 |  | 63% | 7 | 63% | 8 |  | 63% | 9 | 63% | 10
64% | 1 | 64% | 2 |  | 64% | 3 | 64% | 4 |  | 64% | 5 | 64% | 6 |  | 64% | 7 | 64% | 8 |  | 64% | 9 | 64% | 10
65% | 1 | 65% | 2 |  | 65% | 3 | 65% | 4 |  | 65% | 5 | 65% | 6 |  | 65% | 7 | 65% | 8 |  | 65% | 9 | 65% | 10
66% | 1 | 66% | 2 |  | 66% | 3 | 66% | 4 |  | 66% | 5 | 66% | 6 |  | 66% | 7 | 66% | 8 |  | 66% | 9 | 66% | 10
67% | 1 | 67% | 2 |  | 67% | 3 | 67% | 4 |  | 67% | 5 | 67% | 6 |  | 67% | 7 | 67% | 8 |  | 67% | 9 | 67% | 10
68% | 1 | 68% | 2 |  | 68% | 3 | 68% | 4 |  | 68% | 5 | 68% | 6 |  | 68% | 7 | 68% | 8 |  | 68% | 9 | 68% | 10
69% | 1 | 69% | 2 |  | 69% | 3 | 69% | 4 |  | 69% | 5 | 69% | 6 |  | 69% | 7 | 69% | 8 |  | 69% | 9 | 69% | 10
70% | 1 | 70% | 2 |  | 70% | 3 | 70% | 4 |  | 70% | 5 | 70% | 6 |  | 70% | 7 | 70% | 8 |  | 70% | 9 | 70% | 10
71% | 1 | 71% | 2 |  | 71% | 3 | 71% | 4 |  | 71% | 5 | 71% | 6 |  | 71% | 7 | 71% | 8 |  | 71% | 9 | 71% | 10
72% | 1 | 72% | 2 |  | 72% | 3 | 72% | 4 |  | 72% | 5 | 72% | 6 |  | 72% | 7 | 72% | 8 |  | 72% | 9 | 72% | 10
73% | 1 | 73% | 2 |  | 73% | 3 | 73% | 4 |  | 73% | 5 | 73% | 6 |  | 73% | 7 | 73% | 8 |  | 73% | 9 | 73% | 10
74% | 1 | 74% | 2 |  | 74% | 3 | 74% | 4 |  | 74% | 5 | 74% | 6 |  | 74% | 7 | 74% | 8 |  | 74% | 9 | 74% | 10
75% | 1 | 75% | 2 |  | 75% | 3 | 75% | 4 |  | 75% | 5 | 75% | 6 |  | 75% | 7 | 75% | 8 |  | 75% | 9 | 75% | 10
76% | 1 | 76% | 2 |  | 76% | 3 | 76% | 4 |  | 76% | 5 | 76% | 6 |  | 76% | 7 | 76% | 8 |  | 76% | 9 | 76% | 10
77% | 1 | 77% | 2 |  | 77% | 3 | 77% | 4 |  | 77% | 5 | 77% | 6 |  | 77% | 7 | 77% | 8 |  | 77% | 9 | 77% | 10
78% | 1 | 78% | 2 |  | 78% | 3 | 78% | 4 |  | 78% | 5 | 78% | 6 |  | 78% | 7 | 78% | 8 |  | 78% | 9 | 78% | 10
79% | 1 | 79% | 2 |  | 79% | 3 | 79% | 4 |  | 79% | 5 | 79% | 6 |  | 79% | 7 | 79% | 8 |  | 79% | 9 | 79% | 10
80% | 1 | 80% | 2 |  | 80% | 3 | 80% | 4 |  | 80% | 5 | 80% | 6 |  | 80% | 7 | 80% | 8 |  | 80% | 9 | 80% | 10
81-100% |  |  |  |  | 81-100% |  |  |  |  | 81-100% |  |  |  |  | 81-100% |  |  |  |  | 81-100%
Prob | Impact | Prob | Impact | Result | Prob | Impact | Prob | Impact | Result | Prob | Impact | Prob | Impact | Result | Prob | Impact | Prob | Impact | Result | Prob | Impact | Prob | Impact | Result
81% | 1 | 81% | 2 | 0 | 81% | 3 | 81% | 4 | 0 | 81% | 5 | 81% | 6 | 0 | 81% | 7 | 81% | 8 | 0 | 81% | 9 | 81% | 10 | 0
82% | 1 | 82% | 2 |  | 82% | 3 | 82% | 4 |  | 82% | 5 | 82% | 6 |  | 82% | 7 | 82% | 8 |  | 82% | 9 | 82% | 10
83% | 1 | 83% | 2 |  | 83% | 3 | 83% | 4 |  | 83% | 5 | 83% | 6 |  | 83% | 7 | 83% | 8 |  | 83% | 9 | 83% | 10
84% | 1 | 84% | 2 |  | 84% | 3 | 84% | 4 |  | 84% | 5 | 84% | 6 |  | 84% | 7 | 84% | 8 |  | 84% | 9 | 84% | 10
85% | 1 | 85% | 2 |  | 85% | 3 | 85% | 4 |  | 85% | 5 | 85% | 6 |  | 85% | 7 | 85% | 8 |  | 85% | 9 | 85% | 10
86% | 1 | 86% | 2 |  | 86% | 3 | 86% | 4 |  | 86% | 5 | 86% | 6 |  | 86% | 7 | 86% | 8 |  | 86% | 9 | 86% | 10
87% | 1 | 87% | 2 |  | 87% | 3 | 87% | 4 |  | 87% | 5 | 87% | 6 |  | 87% | 7 | 87% | 8 |  | 87% | 9 | 87% | 10
88% | 1 | 88% | 2 |  | 88% | 3 | 88% | 4 |  | 88% | 5 | 88% | 6 |  | 88% | 7 | 88% | 8 |  | 88% | 9 | 88% | 10
89% | 1 | 89% | 2 |  | 89% | 3 | 89% | 4 |  | 89% | 5 | 89% | 6 |  | 89% | 7 | 89% | 8 |  | 89% | 9 | 89% | 10
90% | 1 | 90% | 2 |  | 90% | 3 | 90% | 4 |  | 90% | 5 | 90% | 6 |  | 90% | 7 | 90% | 8 |  | 90% | 9 | 90% | 10
91% | 1 | 91% | 2 |  | 91% | 3 | 91% | 4 |  | 91% | 5 | 91% | 6 |  | 91% | 7 | 91% | 8 |  | 91% | 9 | 91% | 10
92% | 1 | 92% | 2 |  | 92% | 3 | 92% | 4 |  | 92% | 5 | 92% | 6 |  | 92% | 7 | 92% | 8 |  | 92% | 9 | 92% | 10
93% | 1 | 93% | 2 |  | 93% | 3 | 93% | 4 |  | 93% | 5 | 93% | 6 |  | 93% | 7 | 93% | 8 |  | 93% | 9 | 93% | 10
94% | 1 | 94% | 2 |  | 94% | 3 | 94% | 4 |  | 94% | 5 | 94% | 6 |  | 94% | 7 | 94% | 8 |  | 94% | 9 | 94% | 10
95% | 1 | 95% | 2 |  | 95% | 3 | 95% | 4 |  | 95% | 5 | 95% | 6 |  | 95% | 7 | 95% | 8 |  | 95% | 9 | 95% | 10
96% | 1 | 96% | 2 |  | 96% | 3 | 96% | 4 |  | 96% | 5 | 96% | 6 |  | 96% | 7 | 96% | 8 |  | 96% | 9 | 96% | 10
97% | 1 | 97% | 2 |  | 97% | 3 | 97% | 4 |  | 97% | 5 | 97% | 6 |  | 97% | 7 | 97% | 8 |  | 97% | 9 | 97% | 10
98% | 1 | 98% | 2 |  | 98% | 3 | 98% | 4 |  | 98% | 5 | 98% | 6 |  | 98% | 7 | 98% | 8 |  | 98% | 9 | 98% | 10
99% | 1 | 99% | 2 |  | 99% | 3 | 99% | 4 |  | 99% | 5 | 99% | 6 |  | 99% | 7 | 99% | 8 |  | 99% | 9 | 99% | 10
100% | 1 | 100% | 2 |  | 100% | 3 | 100% | 4 |  | 100% | 5 | 100% | 6 |  | 100% | 7 | 100% | 8 |  | 100% | 9 | 100% | 10